## Sheet1
Town Branch Commons Detailed Project Schedule
Activity | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Program Manager (PM) Notice to Proceed
PM - Work Order #1
Community Engagement - Work Order #6
KYTC Fully Executed MOA CMAQ (Zone 1)
KYTC Fully Executed MOA TAP (Zone 2)
Surveying - Work Order #2
Develop Project Basemapping
Technical Advisory Group Meeting No. 1
KYTC Approval of TBC RFQ/RFP
Advertise TBC Design RFQ/RFP
Pre-Proposal Meeting
TBC Design Consultant Selection
TBC Design Consultant Phase I NTP
NEPA - Work Order #3
Grant Management - Work Order #4
2016 TIGER Grant Application
TIGER Obligation Deadline
Phase I Design Phase
Phase I Design - Traffic Analysis
Phase I - Develop Initial Alternatives
Technical Advisory Group Meeting No. 2
KU Transmission Coordination Meeting
Phase I - Project Team Meeting - Align. Review
Phase I - Value Engineering Study
Phase I - Preliminary Line and Grade Inspection
Technical Advisory Group Meeting No. 3
KYTC Supplemental MOA (Phase II Design)
Phase II Design Phase
Phase II Design - Joint Inspection
Phase II Design - R/W Plans Due
KYTC Supplemental MOA (RUC Phase)
Right of Way Phase (Appraisal/Acquisition)
Utility Coordination - Work Order #5
Utility Relocation - LFUCG Sewer Work Phase
Utility Relocation - LFUCG Sewer Work Design
Utility Relocation - LFUCG Sewer Construction
Utility Relocation Work - Other than LFUCG - TBD
Construction Pre-Bid Meeting
Construction Letting - Zone 1-4
Construction Phase - Zone 1-4